## Start
Owner Builder in a Box: Owner Workbook
Your whole owner-build in one spreadsheet. Works offline in Excel, Numbers, LibreOffice or Google Sheets (offline mode).
Includes Guides and common Q&A for tracking your project efficiently
How it works
Colours | White cells are for you. Grey cells are calculated and locked so they can't be typed over by accident (Review > Unprotect sheet if you need to; there's no password). Pale yellow rows are examples: delete them when you're ready (the Dashboard counts what's left).
Start here | 1. Fill in the Project tab. 2. Set your budgets on Packages. 3. Work through Compliance and Gateways from G0. 4. Log everything else as it happens.
Files | Documents live in Google Drive, not in the workbook. Register each one on the Documents tab: it builds a Doc ID (e.g. 02-DWG-012), the file name to use, and the Drive folder to save it in. Paste the Drive link once it's uploaded. Share documents, photos and tender documents with trades and others as needed. (recommend to use suggested naming conventions for files)
Offline | Excel / Numbers / LibreOffice: open this file and work. With Google Drive / Dropbox / Onedrive for desktop the project folder is on your computer too, so you can save files offline and they sync later. Google Sheets: turn on Drive > Settings > Offline, or in the Sheets app tap ⋮ > Make available offline. The Apps Script menu needs a connection.
Folder links | The Open links work with Google Drive, Dropbox, OneDrive or SharePoint: paste each folder's link (Share > Copy link) into the Google Drive Map tab. Working offline on a computer, paste the local folder path instead and it opens without internet.
Google Sheets fast set-up | Upload this file to Drive, open it, then File > Save as Google Sheets. Then Extensions > Apps Script, paste in Code.gs, save and reload. A new Owner Builder menu appears: Set up Drive folders creates the folder tree for this build and links every folder path in the workbook.
Need more rows? | Each tab has room for hundreds of entries. If you run out, unprotect the sheet and copy the last row down so the formulas come too. The Dashboard warns if anything is typed below the last formula row.
Tabs
Dashboard | Current gateway, money, compliance progress and everything that needs attention.
Project | Address, title, owners, budget, permits, site classification.
Guides / Q&A / Reference | Buying guides, plain-English answers and key numbers from Owner Builder in a Box. Read-only.
Gate Review | G0 to G7: progress against entry, deliverables and exit checks, with your Go / Hold / Stop decision.
Gateways | Every entry criterion, deliverable and exit check for each gate.
Compliance | The 11-stage Victorian owner-builder checklist, with the folder to file the evidence in.
Risks | Starter risk register with likelihood × impact ratings.
Google Drive Map | The folder tree, what goes in each folder, the file naming rules, and the folder links.
Rooms | Room sizes give floor area, paint area, skirting length and tile quantities. Area type keeps garages and outdoor areas out of the paint and skirting figures.
Selections | Every product decision: spec, supplier, price, status.
Diary | Site diary, plan notes, instructions to trades, defects, questions for the building surveyor.
Photos | Log of site photos, especially before anything is covered.
Documents | The register of every file in Google Drive, with Doc IDs and file names.
Tender Setup / Tenders | Quote comparison: compliance gates, price levelling, weighted scoring and a recommendation per package.
Packages | 20 trade packages: budget, committed, paid and forecast.
Trades | Contacts, licences, insurance, SWMS, contracts, deposit checks, expiry alerts.
Variations / Payments | Written variations and every invoice. They feed the Packages costs.
Certificates | Mandatory inspections and the certificates needed for the final inspection.
Settings | The legal thresholds and rules behind the checks (deposit caps, contract, warranty and consent thresholds, warning days). Update them here when the law changes.
Important
Not advice | General information only. It is not legal, financial or building advice. Always confirm current requirements with the Building and Plumbing Commission (BPC), your relevant building surveyor, your council and WorkSafe Victoria. Victorian rules checked September 2026.

## Dashboard
Dashboard
Where the build is up to. Everything here is calculated; change the other tabs, not this one.
Project
Project
Current gateway
Exit checks done at this gate
Ready to pass?
Money
Total budget
Contingency in the budget
Allocated to packages |  |  |  |  | Sum of Packages budgets. Should be about the total budget less contingency.
Committed (contracts + approved variations)
Committed as % of package budgets |  |  |  |  | G3 exit check: compare with the target on Settings before going to site.
G3 target
Spent to date (paid)
Budget used
Forecast final cost
Forecast under / (over) total budget
Selections total
Takeoffs (Rooms tab)
Internal floor area (m²) |  |  |  |  | Blank area type counts as internal.
Garage floor area (m²)
External areas (m²) |  |  |  |  | Driveways, paving, decks.
Wall paint, one coat (m²)
Skirting (m)
Floor covering incl. waste (m²)
Compliance by stage | Items | N/A | Done | % done
1. Eligibility
2. Certificate of consent
3. Site, planning & design
4. Building permit & pre-start
5. Health & safety (WorkSafe Victoria)
6. Insurance
7. Engaging trades
8. During construction
9. Completion & occupancy
10. Records & selling
11. Finance & tax
All stages
Needs attention | Count
Entries past the pre-filled rows (not counted!) |  |  |  |  | Something was typed below the last formula row. Unprotect the sheet and copy the last row down to extend it.
Go decisions with exit checks open |  |  |  |  | Gate Review tab
Earlier gates without a Go decision |  |  |  |  | Gates before the current gateway on the Project tab.
Certificate of consent needed, no number recorded |  |  |  |  | Budget is over the consent threshold on Settings.
Principal contractor needed, not done |  |  |  |  | Budget is at or over the principal contractor threshold (Compliance oh-pc).
Trade paperwork expired |  |  |  |  | Trades tab: licence or insurance past its expiry date.
Trade paperwork expiring soon |  |  |  |  | Ask for new certificates of currency now.
Trade dates typed as text or missing |  |  |  |  | A date typed as text can't be checked for expiry.
Trade contract checks to look at |  |  |  |  | Trades tab: duplicates, registration and home warranty.
Deposits over the statutory cap |  |  |  |  | Caps and threshold are on Settings.
Quotes needing a look |  |  |  |  | Tenders tab: Check column.
Tender packages tied for 1st |  |  |  |  | Tender Setup tab
Documents with problems |  |  |  |  | Documents tab: Check column.
Packages with naming problems |  |  |  |  | Packages tab: names must start with their No.
Rooms with sizes typed as text
Invoices charging GST from unregistered trades
Unpaid invoices
Open defects |  |  |  |  | Diary tab
Open questions for the building surveyor |  |  |  |  | Diary tab
Pending variations |  |  |  |  | Don't let work start before the price is agreed.
Selections still to choose |  |  |  |  | All selections must be locked before G6.
Packages forecast over budget |  |  |  |  | By more than the margin on Settings.
Tender weights that don't add to 100 |  |  |  |  | Tender Setup tab
Must-have certificates not yet passed |  |  |  |  | Certificates tab. Needed before the final inspection.
High risks still open
Duplicate Doc IDs |  |  |  |  | Documents tab: rows sharing a Doc ID. Should be 0.
Example rows still in the workbook |  |  |  |  | Delete them once you've seen how each tab works.

## Project
Project
The basics, always at hand. Yellow cells are yours to fill in.
Project |  | Notes
Project name
Site address
Lot / plan of subdivision
Title volume / folio
Owner-builder(s)
Phone
Email
Current gateway | G0
Target start
Target finish
Money
Total budget inc GST ($)
Contingency (%) | 12% | 10–15% is typical. Owner-builders often underestimate site works, services and finishes.
Lender
Approvals
Certificate of consent no.
Relevant building surveyor
Building permit no.
Planning permit no. (if any)
Site & design
Soil classification (AS 2870)
Wind classification
BAL rating (if bushfire prone)
Energy rating (stars)
Google Drive
Project folder link |  | Paste your project folder link (any provider), or let Owner Builder > Set up Drive folders fill it in Google Sheets.

## Q&A
Owner-builder Q&A (Victoria)
Plain-English answers, grouped by topic. Read-only. General information, checked September 2026, not legal advice.
Topic | Question | Answer
Getting started | What is an owner-builder? | An owner-builder is a landowner who takes legal responsibility for domestic building work on their own land, instead of engaging a registered builder to manage the whole job. You take on the builder's responsibilities: quality, compliance, safety, and coordinating and paying trades. You can do some work yourself and hire trades for the rest.
Getting started | Do I have to do the building work myself? | No. Most owner-builders act as project manager and engage trades for most of the work. You can do the non-licensed work yourself if you're capable, such as some carpentry, painting or landscaping. Plumbing, gasfitting and electrical work must always be done by licensed practitioners.
Getting started | How much can I really save? | A builder's margin and overheads are commonly 15–25% of the build cost. Realistic owner-builder savings are often 10–20% after allowing for your time, mistakes, higher finance costs and missed trade discounts. Savings come from managing well, not just from cutting out the builder.
Getting started | How long does an owner-build take? | Plan on 18–24 months from idea to occupancy for a typical new home. That's roughly 6–11 months of design, approvals and procurement, then 9–13 months on site. Owner-builders working part-time usually take longer. See the gateways program.
Getting started | What skills do I need? | Organisation matters more than trade skills. You'll be reading plans, scheduling, negotiating, checking quality, managing money and paperwork, and keeping people safe. If you run projects or a household budget well, you're most of the way there. Owner Builder in a Box fills in the rest.
Eligibility & certificate of consent | When do I need a certificate of consent? | When the value of the domestic building work is over $20,000 (it was $16,000 before 1 July 2026). Value means labour plus materials plus GST, including a market value for your own labour. Below that you can owner-build without consent, but you still need any building permit the work requires.
Eligibility & certificate of consent | Who is eligible? | • You own the land, or you're a director of the owning company or a beneficiary of the owning trust • The work is for a single dwelling (or ancillary to it) • You live in it, or intend to (not required for a small second dwelling) • You're not in the business of building • No owner-builder permit in the past 5 years (with exceptions) • You've passed the BPC eLearning assessment and done construction induction training See the eligibility checklist.
Eligibility & certificate of consent | What is the eLearning assessment? | A free online course and assessment run by the Building and Plumbing Commission. It covers your legal responsibilities, safety, contracts and the building process, and takes about 2–3 hours. You need a pass before applying for consent.
Eligibility & certificate of consent | Can I owner-build again within five years? | Generally not on a different property. The exceptions are further work on the same home, building a small second dwelling, or an exemption granted by the BPC for special circumstances such as a substantial change in circumstances or hardship.
Eligibility & certificate of consent | Can I owner-build if my partner and I own the land together? | Yes. Each owner-builder named needs to meet the requirements. The five-year rule also looks at people you co-own, or have co-owned, property with, so check both your histories.
Eligibility & certificate of consent | Can I owner-build a house to sell or rent out? | Owner-builder consent is for a home you live in or intend to live in, apart from a small second dwelling. Building to sell or rent can put you "in the business of building", which requires registration.
Eligibility & certificate of consent | Who regulates owner-builders now: the VBA or the BPC? | The Building and Plumbing Commission (BPC). It replaced the Victorian Building Authority, and from 1 July 2026 it also absorbed domestic building insurance (formerly VMIA) and dispute resolution (formerly DBDRV). Older guides and forms may still say VBA.
Permits & inspections | Do I need a planning permit and a building permit? | You always need a building permit for a new home. You need a planning permit only if your zone or overlays require one, for example heritage, bushfire, flood, vegetation or some neighbourhood character controls. Check your Planning Property Report on VicPlan, and ask council if you're unsure.
Permits & inspections | Who issues the building permit? | A relevant building surveyor (RBS) that you appoint. It can be a private surveyor or the council's. They assess your plans, issue the permit, carry out the mandatory inspections and issue the occupancy permit or certificate of final inspection.
Permits & inspections | What inspections are mandatory? | Usually before pouring footings, before pouring the slab, at frame stage and at final. Your permit may add more, such as a pre-plaster or a retaining wall inspection. You must notify the RBS at each stage and not cover work before it's inspected.
Permits & inspections | What documents does the surveyor need at the end? | Typically: plumbing compliance certificates, Certificate of Electrical Safety, waterproofing, termite and glazing certificates, insulation and energy compliance, smoke alarm certificate, and engineer sign-offs where required. Collect them as each trade finishes and don't release final payment until you have them.
Permits & inspections | What is an occupancy permit and why does it matter? | It's the RBS confirming a new home is suitable to live in. It's an offence to occupy a new dwelling without one, and your lender and insurer will ask for it.
Permits & inspections | What does the 7-star energy rating mean for me? | New Victorian homes must meet NCC 2022 energy efficiency: a 7-star NatHERS thermal rating plus a whole-of-home energy budget covering appliances, hot water and solar. Your energy assessor's report sets the insulation, glazing and fixed appliances, so buy exactly what it says.
Permits & inspections | Can I change the design during construction? | Minor non-structural changes are usually fine. Anything affecting structure, siting, fire safety or energy compliance needs an amended permit from your RBS before you build it.
Trades & contracts | Do my trades need to be registered? | Plumbers and gasfitters must be BPC licensed or registered, and electricians must be licensed by Energy Safe Victoria, regardless of job size. For other domestic building work over $10,000, the trade generally needs to be a registered domestic builder with a written major domestic building contract, with some single-trade exemptions. An increase in that threshold to $20,000 has been proposed.
Trades & contracts | How many quotes should I get? | Three is the minimum per package. Five for big packages like slab, frame and roof. Send every tenderer the same RFQ pack so the prices are comparable, then level and score them with the tender tool.
Trades & contracts | Should I always pick the cheapest quote? | No. Level the quotes first by adding the cost of exclusions and normalising provisional sums. Then weigh price against experience, availability, quality and communication. A quote well below the others usually means something is missing from the scope.
Trades & contracts | How much deposit can a trade ask for? | Under a major domestic building contract: no more than 10% if the contract price is under $20,000, and 5% if it's $20,000 or more. For smaller trade jobs, keep deposits minimal. Pay for completed, inspected work, not in advance.
Trades & contracts | What should be in a trade contract? | Scope tied to drawing revisions, inclusions and exclusions, price and GST, program, payment milestones, variations in writing, defects period, insurance, SWMS and site rules, and compliance certificates required before final payment. See the must-have clauses.
Trades & contracts | What if a trade does defective work? | Document it with photos, notify them in writing with a reasonable time to fix, and meet on site. If it's unresolved, use the BPC's domestic building dispute resolution, then VCAT. Statutory warranties under the Domestic Building Contracts Act protect you.
Trades & contracts | Can I hire workers directly and pay them wages? | You can, but then you're an employer, with obligations for WorkCover insurance, superannuation, PAYG, awards and OHS. Most owner-builders engage trades as contractors with their own ABN and insurance.
Money & finance | Will a bank lend to an owner-builder? | Some will, often with a lower maximum loan-to-value ratio, a detailed costing, fixed-price quotes, and progress draws released only after a valuer inspects each stage. Talk to a broker who knows construction lending before you buy land or commit to a design.
Money & finance | How much contingency should I allow? | At least 10%, and 15% for sloping, rocky or bushfire-prone sites or renovations. Contingency is for risks, not upgrades. Track it separately in your budget.
Money & finance | Can I get the First Home Owner Grant? | Owner-builders building their first home may be eligible, subject to value caps, residence requirements and timing rules such as when the foundations are laid. Check the current rules with the State Revenue Office before you start.
Money & finance | Do I pay or claim GST? | If you're building your own home to live in, you're generally not carrying on an enterprise, so you pay GST on trade invoices but can't claim it back. Building to sell can change that, so get tax advice.
Money & finance | How do I stop the budget blowing out? | Freeze scope at gateway G1. Get fixed prices wherever you can. Use written variations. Track Budget → Committed → Paid → Forecast every week. And never pay ahead of work.
Safety & insurance | Am I responsible for safety on site? | Yes. As the person managing or controlling the site you have duties under the OHS Act 2004. For projects of $350,000 or more you're the principal contractor unless you appoint one. That means a safety coordination plan, site induction, SWMS management and signage.
Safety & insurance | What is a SWMS? | A Safe Work Method Statement is required before any high-risk construction work, such as work at heights over 2 m, trenches over 1.5 m, structural alterations or work near powerlines. The trade prepares it. You check it's on site and being followed.
Safety & insurance | What insurance do I need? | Construction (contract works) insurance and public liability are strongly recommended, and lenders usually require them. Also consider personal accident cover. Check every trade's public liability and WorkCover certificates of currency, and track their expiry dates.
Safety & insurance | Does everyone on site need a white card? | Yes. Anyone doing construction work needs construction induction training, and so do you. It's also part of the owner-builder eligibility criteria.
Selling & after completion | What if I sell within 6.5 years? | Under s137B of the Building Act you must, before signing the contract of sale: (1) get a defects report from a prescribed building practitioner, no more than 6 months old, on the BPC template; and (2) for work over $20,000, comply with the statutory insurance scheme by buying owner-builder cover. The buyer gets copies. Selling without them is an offence, and the buyer may be able to end the contract.
Selling & after completion | What changed for owner-builder insurance on 1 July 2026? | The old last-resort domestic building insurance was replaced by the First Resort Home Warranty Scheme, run by the BPC. Buyers can claim without the owner-builder having died, disappeared or become insolvent. The trigger threshold rose to $20,000.
Selling & after completion | What records should I keep, and for how long? | Keep everything for at least 10 years: permits, stamped plans, certificates, contracts, invoices, warranties, photos and the site diary. A complete handover file makes selling, insurance claims and future renovations much easier. My Build keeps it all in one place.
Selling & after completion | Am I liable for defects after I finish? | If you sell, the buyer can rely on statutory warranties for owner-builder work for a period, and the insurance scheme backs claims. In practice that's why the defects report and insurance exist. Build it right, document it, and fix issues before sale.

## Guides
Buying guides & specs
Stage-by-stage: the standards that apply, the spec to confirm and what to ask suppliers. Read-only. Content checked September 2026.
Stage | Topic | Standards | Spec to confirm | Ask the supplier / trade
Base stage | Concrete footings & slab | AS 2870 (residential slabs & footings), AS 3600 (concrete structures). | • Spec to confirm with your engineer: slab type (waffle or raft), concrete strength (typically N20–N32 MPa), slump, mesh (e.g. SL82), bar sizes, edge beam depths, cover to steel. • Vapour barrier: 0.2 mm polyethylene, lapped and taped. Check the energy report for slab-edge insulation. • Termite management to AS 3660.1: physical barrier or chemical. Get the certificate and durable notice. | Is pump hire included? What's the allowance for over-dig and extra concrete? Who books the pre-pour inspection? Will you give me delivery dockets showing MPa?
Base stage | Site drainage & stormwater |  | • Pipe class and diameter per the engineer's drainage plan (commonly 90 mm and 100 mm PVC). • Rainwater tank size if your energy or water compliance relies on it (often 2,000 L or more connected to toilets or laundry). • Connection to the legal point of discharge. Your plumber lodges a compliance certificate.
Frame & roof | Wall frames & roof trusses | AS 1684 (timber framing), AS 4440 (nail-plated trusses), NASH standard for light steel. | • Timber grade: MGP10 / MGP12 pine is standard. Use H2 treated in termite zones, or light-gauge steel. • Wind classification (e.g. N2, N3) from your engineer. It drives tie-downs and bracing. • Get the frame & truss layout, design certificate and bracing plan with the delivery. | Is it pre-cut or prefabricated? Are lintels, beams and bracing included? What's the lead time? Do you set out the trusses on site?
Frame & roof | Roofing: metal or tiles | AS 1562.1 (metal roofing), AS 2050 (tiles), AS 3959 (bushfire). | • Metal: 0.42 mm BMT is standard. Choose the colour's solar absorptance to match the energy report. • Anticon or sarking blanket for thermal and condensation control (NCC 2022 condensation rules). • Gutter overflow provisions and downpipe spacing per AS/NZS 3500.3. • BAL-rated ember guards and screens if you're in a bushfire prone area.
Lock-up | Windows & external doors | AS 2047 (windows), AS 1288 (glass selection), AS 3959 (BAL). | • Use the U-value and SHGC in your energy report. They are part of your 7-star compliance and must be matched. • Double glazing in thermally broken or uPVC frames is typical for 7-star compliance in Victoria. • Wind rating to match the site's wind class. BAL rating if required. • Keep the WERS label and AS 2047 certificate for your building surveyor. | Do these U-value and SHGC figures match my energy report? What's the lead time? Are flashings and reveals included? Is there a warranty on hardware and seals?
Lock-up | Wall wrap, cladding & bricks |  | • Vapour-permeable wall wrap (NCC 2022 condensation provisions). Check its class against the specification. • Bricks: order about 5% extra from the same batch to avoid colour variation. Check wall ties and weep holes. • Fibre cement, timber or metal cladding: fix it to the manufacturer's installation guide. Warranties depend on it.
Services | Insulation |  | Standard: AS/NZS 4859.1. Values come from your energy report. • Typical Victorian 7-star: ceiling around R6.0, external walls around R2.5, plus underfloor if the floor is suspended. • Photograph every wall before plaster. The building surveyor may ask for an installation certificate.
Services | Hot water, heating & all-electric homes |  | • New Victorian homes that need a planning permit (applied for from 1 January 2024) can't connect to reticulated gas. All-electric is the default choice anyway. • A heat-pump hot water system scores well in the NCC 2022 whole-of-home energy budget. • Reverse-cycle split or ducted systems: check the energy rating, zoning and the refrigerant licence (ARCtick) of the installer. • Solar PV: use a Solar Accreditation Australia (formerly CEC) accredited installer if you want rebates. Check Solar Victoria.
Services | Electrical: switchboard, lighting, smoke alarms | AS/NZS 3000 (wiring rules), AS 3786 (smoke alarms). | • RCD (safety switch) protection on all final sub-circuits. • Hardwired, interconnected smoke alarms in the locations the NCC requires. • Plan the points before rough-in: walk every room in My Build and note GPOs, switches, data and TV. • Think ahead: an EV charger circuit, induction cooktop capacity, battery-ready switchboard.
Services | Plumbing fixtures & tapware |  | • Only buy WaterMark-certified products. Plumbers can refuse to install anything else, and it may not pass inspection. • Check WELS water ratings (star rating and litres per minute). • Hot water to bathrooms must be delivered at a maximum of 50°C (tempering or thermostatic valve per AS/NZS 3500.4).
Fit-out | Wet areas: waterproofing & tiles |  | Standard: AS 3740 (waterproofing of domestic wet areas). • Get a waterproofing certificate for every wet area. The building surveyor needs it. • Slip resistance: use P3 or better for wet-area floors and P4–P5 for outdoor areas (AS 4586). • Order about 10% extra tiles from one batch (15% for diagonal or herringbone). My Build's room calculator does this for you.
Fit-out | Kitchen, benchtops & joinery |  | • Engineered stone is banned in Australia from 1 July 2024. Consider porcelain, sintered stone, natural stone, laminate or timber. • Board: E0 / E1 low-formaldehyde, moisture-resistant under sinks. • Sign off shop drawings. Check the appliance cut-out sizes and ventilation clearances first. • Appliances: use the Energy Rating label, and check the cooktop's electrical load with your electrician.
Fit-out | Paint, flooring & finishes |  | • Low-VOC, washable paints for living areas. Mould-resistant paint for wet areas. Record the colour codes in My Build. • Flooring: acclimatise timber before laying. Check the moisture content of the slab. • Keep every product's warranty registration and care guide for the handover file.
How to buy | Getting trade pricing as an owner-builder |  | • Open trade accounts with your building permit and certificate of consent. Many suppliers give owner-builders a builder's discount. • Bundle orders by stage (e.g. all frame hardware together) and ask for a project price. • Compare supply-only prices against supply & install quotes using the tender tool.
How to buy | Deliveries, storage & checking goods |  | • Time deliveries to the program. Early deliveries get stolen or damaged; late ones stop trades. • Check quantities and condition on arrival and note damage on the docket before you sign it. • Store off the ground, covered and secure. Photograph deliveries for insurance. • Keep every docket and invoice against its trade package in your budget.

## Reference
Reference
Key numbers, contract types, tendering and who does what. Read-only.
Key numbers
Rule | Figure | Where it comes from
Certificate of consent required | Work over $20,000 (was $16,000 before 1 July 2026) | Building Act 1993, BPC
Owner-builder permit frequency | 1 every 5 years (exemptions apply) | Building Act s25E, BPC
Major domestic building contract / registered builder | Work over $10,000 (proposed increase to $20,000) | Domestic Building Contracts Act 1995
Principal contractor (OHS) | Projects of $350,000 or more | OHS Regulations 2017
Selling: defects report & insurance | Within 6 yrs 6 mths of completion. Report ≤ 6 months old | Building Act s137B
Energy efficiency (new homes) | 7-star NatHERS + whole-of-home | NCC 2022, Victoria from 1 May 2024
Building permit levy | Work over $10,000 | Building Act, collected by the RBS
Contract types
Type | How it's priced | Best for | Watch out for
Lump sum (fixed price) | One price for a defined scope | Well-documented packages: slab, roof, electrical | Vague scope means variations. Exclusions hide cost.
Schedule of rates | $ per m², per point, per 1,000 bricks | Measurable work: bricks, plaster, tiles | You carry the quantity risk. Measure it yourself.
Labour only | Labour price; you supply the materials | Carpentry, fixing, painting | You carry material risk and waste. Deliveries must be on time.
Supply only | Materials delivered | Frames, trusses, windows, appliances | Check against the plans. Delivery dates. Damage on delivery.
Supply & install | Materials + labour | Roofing, insulation, cabinetry | Confirm the spec and brand. Warranty covers both parts.
Cost plus / do & charge | Actual cost + margin or hourly rate | Small unknowns, repairs, excavation in rock | No price certainty. Cap it and require daily dockets.
What goes in an RFQ pack
What goes in an RFQ pack
Cover letter: package, address, closing date, contact
Scope of works + inclusions list
Drawings & specification (with revision numbers)
Engineering & energy report extracts
Program: target start and duration
Site info: access, power, water, slope, photos
Your draft trade agreement (see Contracts)
Pricing schedule so every quote breaks down the same way
What to return: licence, insurance, ABN, SWMS, references
Levelling: making quotes comparable
Levelling: making quotes comparable
Exclusions: if Quote A excludes rubbish removal, add what it will cost you
Provisional sums: replace each tenderer's allowance with the same figure
Scope gaps: price anything missing against the RFQ
Risk: add an allowance for vague or heavily qualified quotes
GST: compare everything inc. GST
Result: a levelled price for each tenderer, like-for-like
Red flags
Red flags
Price more than 15% under the median: something is probably missing
Deposit request above the statutory cap
No written quote, or "cash price"
Registration or insurance in a different name
Long exclusions list or "subject to" everywhere
Can't provide references or recent jobs
Pressure to sign immediately
1. Tenderers & quotes + Add tenderer Export CSV Print Reset to example 2. Criteria weights 3. Results How the scoring works
1. Tenderers & quotes + Add tenderer Export CSV Print Reset to example 2. Criteria weights 3. Results How the scoring works
Compliance gates are pass / fail. A tenderer who fails any gate (not registered, no current insurance, no SWMS, non-conforming scope) is excluded from ranking, whatever the price.
Levelled price = quoted price + cost of exclusions + provisional sum adjustment + risk allowance.
Price score = lowest compliant levelled price ÷ this levelled price × 10. The cheapest scores 10.
Non-price criteria are scored 0–10 by you: experience, program, quality, communication, warranty.
Weighted total = Σ (score × weight) ÷ 10, out of 100. Weights must add to 100%.
Quotes more than 15% below the median levelled price are flagged Check scope.
Who does what (RACI)
Activity | You (owner-builder) | Designer / engineer | Building surveyor | Trades | Lender
Design brief & scope | A/R | C | I | – | I
Working drawings & engineering | A | R | C | – | I
Certificate of consent | A/R | – | I | – | I
Building permit | A | C | R | – | I
Tendering & contracts | A/R | C | – | C | I
Site safety & coordination | A/R | – | – | R (own work) | –
Mandatory inspections | A (notify) | C | R | C | I
Trade workmanship & certificates | A | – | C | R | –
Progress claims & payments | A/R | – | – | C | R (drawdown)
Occupancy permit | A | – | R | C | I

## Gate Review
Gate review
At each gate decide Go, Hold or Stop. A gate is ready when every exit check on the Gateways tab is Yes.
Gate | Name | Purpose | Entry criteria met | Deliverables done | Exit checks | Exit checks done | Exit % | Ready to pass? | Decision | Decision check | Decision date | Decision guide | Typical budget spent | Typical duration | Notes
G0 | Feasibility & eligibility | Can I, should I, and can I afford to owner-build? | [9 empty] | Go to concept, or Stop and consider a builder or part-build instead. | ~0–1% | 1–3 months (with G1)
G1 | Concept & budget | Lock the brief, the concept and the money. | [9 empty] | Go to detailed design, or Hold and value-manage the concept. | ~2–3% | 1–3 months (with G0)
G2 | Design & approvals | Everything you need for a building permit. | [9 empty] | Go to procurement, or Hold for design changes. | ~5% | 2–6 months
G3 | Procurement & permit | Right trades, right price, right paperwork. Ready to start. | [9 empty] | Go to site, or Hold until the price and paperwork are right. | ~8% | 1–2 months
G4 | Site works & base | Out of the ground: set-out, services, footings and slab. | [9 empty] | Go to frame. | ~15–20% | 4–8 weeks
G5 | Frame & lock-up | Structure, roof, windows and doors. Weather-tight and secure. | [9 empty] | Go to fit-out. | ~45–55% | 8–12 weeks
G6 | Fit-out & fixing | Plaster to paint, wet areas, kitchen, fit-off. | [9 empty] | Go to final. | ~85–90% | 12–20 weeks
G7 | Completion & handover | Occupancy, close-out and your handover file. | [9 empty] | Close the project. Welcome home. | 100% | 2–6 weeks

## Gateways
Gateways G0 to G7
Tick each entry criterion, deliverable and exit check as it's met. A gate is ready to pass when every exit check is Yes (see Gate Review).
Gate | Gate name | Type | Item | Done? | Date | Evidence Doc ID | Drive folder (suggested) | Folder | Notes
G0 | Feasibility & eligibility | Entry criteria | You own, or are buying, the land
G0 | Feasibility & eligibility | Entry criteria | You have a rough idea of the home you want
G0 | Feasibility & eligibility | Entry criteria | You know how much time you can commit each week
G0 | Feasibility & eligibility | Deliverable | Eligibility self-check (s25E) |  |  |  | 01 Eligibility, Land & Planning
G0 | Feasibility & eligibility | Deliverable | Title, zoning & overlay review |  |  |  | 01 Eligibility, Land & Planning
G0 | Feasibility & eligibility | Deliverable | Order-of-magnitude budget ($/m² × area) |  |  |  | 03 Permits, Insurance & Finance
G0 | Feasibility & eligibility | Deliverable | Finance conversation with an owner-builder-friendly lender |  |  |  | 03 Permits, Insurance & Finance
G0 | Feasibility & eligibility | Deliverable | Honest skills & time assessment |  |  |  | 00 Project Register
G0 | Feasibility & eligibility | Exit check | Eligible, or exemption pathway known
G0 | Feasibility & eligibility | Exit check | No title or planning showstoppers
G0 | Feasibility & eligibility | Exit check | Budget and finance roughly align
G0 | Feasibility & eligibility | Exit check | Household agrees on time, stress and risk
G1 | Concept & budget | Entry criteria | G0 passed
G1 | Concept & budget | Entry criteria | Designer or architect engaged
G1 | Concept & budget | Entry criteria | Feature & level survey and soil test ordered
G1 | Concept & budget | Deliverable | Written design brief (rooms, sizes, must-haves, nice-to-haves) |  |  |  | 02 Design & Engineering
G1 | Concept & budget | Deliverable | Concept plans & room schedule in My Build |  |  |  | 02 Design & Engineering
G1 | Concept & budget | Deliverable | Elemental cost plan with 10–15% contingency |  |  |  | 03 Permits, Insurance & Finance
G1 | Concept & budget | Deliverable | Finance pre-approval |  |  |  | 03 Permits, Insurance & Finance
G1 | Concept & budget | Deliverable | Draft program (target start & finish) |  |  |  | 00 Project Register
G1 | Concept & budget | Deliverable | First risk register |  |  |  | 00 Project Register
G1 | Concept & budget | Exit check | Concept fits the budget, including contingency
G1 | Concept & budget | Exit check | Concept fits the site (setbacks, overlays, fall, BAL)
G1 | Concept & budget | Exit check | Scope frozen: changes after this cost money
G2 | Design & approvals | Entry criteria | G1 passed, scope frozen
G2 | Design & approvals | Entry criteria | Owner-builder eLearning & white card done
G2 | Design & approvals | Deliverable | Working drawings & specification |  |  |  | 02 Design & Engineering
G2 | Design & approvals | Deliverable | Engineering: footings, slab, frame, drainage |  |  |  | 02 Design & Engineering
G2 | Design & approvals | Deliverable | 7-star energy report |  |  |  | 02 Design & Engineering
G2 | Design & approvals | Deliverable | BAL assessment (if bushfire prone) |  |  |  | 02 Design & Engineering
G2 | Design & approvals | Deliverable | Planning permit (if required) |  |  |  | 01 Eligibility, Land & Planning
G2 | Design & approvals | Deliverable | Certificate of consent from the BPC |  |  |  | 01 Eligibility, Land & Planning
G2 | Design & approvals | Deliverable | Legal point of discharge, easement consents |  |  |  | 01 Eligibility, Land & Planning
G2 | Design & approvals | Exit check | All documents consistent (drawings = engineering = energy)
G2 | Design & approvals | Exit check | Certificate of consent issued
G2 | Design & approvals | Exit check | RBS appointed and fee agreed
G2 | Design & approvals | Exit check | Cost plan updated to the detailed design
G3 | Procurement & permit | Entry criteria | G2 passed
G3 | Procurement & permit | Entry criteria | Trade packages defined with a scope for each
G3 | Procurement & permit | Deliverable | RFQ packs issued (3 quotes per package) |  |  |  | 04 Trades & Tenders
G3 | Procurement & permit | Deliverable | Tender comparison & recommendation per package (tool) |  |  |  | 04 Trades & Tenders
G3 | Procurement & permit | Deliverable | Signed trade contracts (guide) |  |  |  | 04 Trades & Tenders
G3 | Procurement & permit | Deliverable | Trade register: licences, insurance, SWMS |  |  |  | 04 Trades & Tenders
G3 | Procurement & permit | Deliverable | Building permit issued |  |  |  | 03 Permits, Insurance & Finance
G3 | Procurement & permit | Deliverable | Asset protection permit, insurances, site set-up plan |  |  |  | 03 Permits, Insurance & Finance
G3 | Procurement & permit | Deliverable | Baseline program & budget |  |  |  | 03 Permits, Insurance & Finance
G3 | Procurement & permit | Exit check | At least 80% of the budget is committed under contract or firm quote
G3 | Procurement & permit | Exit check | Every early trade has compliant paperwork
G3 | Procurement & permit | Exit check | Permit, consent & insurances in place
G3 | Procurement & permit | Exit check | Finance drawdown schedule agreed with the lender
G4 | Site works & base | Entry criteria | G3 passed
G4 | Site works & base | Entry criteria | Before You Dig done, site fenced, sign up, toilet on site
G4 | Site works & base | Deliverable | Surveyor set-out |  |  |  | 02 Design & Engineering
G4 | Site works & base | Deliverable | Site cut, drainage & underslab plumbing (PCC) |  |  |  | 07 Inspections & Certificates
G4 | Site works & base | Deliverable | Hold point: footing / pre-slab inspection |  |  |  | 07 Inspections & Certificates
G4 | Site works & base | Deliverable | Slab poured, termite management installed |  |  |  | 00 Project Register
G4 | Site works & base | Deliverable | Site diary & photos of everything before it's covered |  |  |  | 06 Site Diary & Photos
G4 | Site works & base | Exit check | RBS inspections passed and certificates filed
G4 | Site works & base | Exit check | Engineer's sign-off (if required)
G4 | Site works & base | Exit check | Cost to date within ±5% of the baseline
G5 | Frame & lock-up | Entry criteria | G4 passed
G5 | Frame & lock-up | Entry criteria | Frame, truss & window orders confirmed against the plans
G5 | Frame & lock-up | Deliverable | Wall frames, trusses, bracing, tie-downs |  |  |  | 02 Design & Engineering
G5 | Frame & lock-up | Deliverable | Hold point: frame inspection (plus engineer if required) |  |  |  | 07 Inspections & Certificates
G5 | Frame & lock-up | Deliverable | Roof, gutters, fascia, sarking |  |  |  | 00 Project Register
G5 | Frame & lock-up | Deliverable | Windows & external doors, wrap, cladding |  |  |  | 02 Design & Engineering
G5 | Frame & lock-up | Deliverable | Services rough-in: plumbing, electrical, data, HVAC |  |  |  | 00 Project Register
G5 | Frame & lock-up | Exit check | Frame inspection passed
G5 | Frame & lock-up | Exit check | Lock-up reached (lender progress draw)
G5 | Frame & lock-up | Exit check | Rough-in certificates, insulation installed & photographed
G6 | Fit-out & fixing | Entry criteria | G5 passed
G6 | Fit-out & fixing | Entry criteria | All selections locked in My Build (tiles, taps, appliances, paint)
G6 | Fit-out & fixing | Deliverable | Plaster, cornice, internal doors, architraves |  |  |  | 00 Project Register
G6 | Fit-out & fixing | Deliverable | Waterproofing (certificate) & tiling |  |  |  | 07 Inspections & Certificates
G6 | Fit-out & fixing | Deliverable | Cabinetry, benchtops, joinery |  |  |  | 00 Project Register
G6 | Fit-out & fixing | Deliverable | Painting |  |  |  | 00 Project Register
G6 | Fit-out & fixing | Deliverable | Plumbing & electrical fit-off (PCC & Certificate of Electrical Safety) |  |  |  | 07 Inspections & Certificates
G6 | Fit-out & fixing | Deliverable | Floor coverings |  |  |  | 00 Project Register
G6 | Fit-out & fixing | Exit check | All compliance certificates collected
G6 | Fit-out & fixing | Exit check | Own defects walk-through done, list issued to trades
G6 | Fit-out & fixing | Exit check | Budget forecast to complete is confirmed
G7 | Completion & handover | Entry criteria | G6 passed
G7 | Completion & handover | Entry criteria | Defects closed out, site cleaned
G7 | Completion & handover | Deliverable | Hold point: final inspection |  |  |  | 07 Inspections & Certificates
G7 | Completion & handover | Deliverable | Occupancy permit / certificate of final inspection |  |  |  | 08 Handover, Records & Sale
G7 | Completion & handover | Deliverable | Utilities, driveway, landscaping, asset bond refund |  |  |  | 03 Permits, Insurance & Finance
G7 | Completion & handover | Deliverable | Handover file: permits, certificates, warranties, as-builts |  |  |  | 08 Handover, Records & Sale
G7 | Completion & handover | Deliverable | Final cost report & lessons learned |  |  |  | 08 Handover, Records & Sale
G7 | Completion & handover | Exit check | Occupancy permit issued before move-in
G7 | Completion & handover | Exit check | All trades paid, retentions released per contract
G7 | Completion & handover | Exit check | Warranty & defects-period reminders set

## Compliance
Victorian owner-builder compliance
Every item from the 11-stage checklist. Set Status as you go; use N/A only where the item genuinely doesn't apply to your build.
ID | Stage | Item | Requirement | What it means | Gateway | Status | Date done | Reference / permit no. | Evidence Doc ID | Drive folder | Folder | Notes
el-own | 1. Eligibility | You own the land | Must | Or you're a director of the company, or a beneficiary of the trust, that owns it. Your name must match the title. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-single | 1. Eligibility | The work relates to a single domestic dwelling | Must | This includes work ancillary to it, such as a garage, shed, pool or deck. Multi-unit developments are out. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-reside | 1. Eligibility | You live in it, or intend to live in it | Must | A small second dwelling on the same lot is exempt from this rule. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-business | 1. Eligibility | You're not in the "business of building" | Must | Owner-building repeatedly for profit is treated as running a building business and needs registration. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-5yr | 1. Eligibility | No owner-builder permit in the last 5 years | Must | This applies to you and to anyone you co-own, or have co-owned, property with. Small second dwellings and further work on the same home are exceptions. The BPC can grant exemptions for special circumstances such as hardship. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-elearn | 1. Eligibility | Pass the BPC owner-builder eLearning assessment | Must | Free and online, about 2–3 hours. Download and keep your pass certificate. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
el-white | 1. Eligibility | Complete construction induction training (white card) | Must | It's part of the eligibility criteria. Anyone else working on your site needs one too. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
co-value | 2. Certificate of consent | Estimate the full value of the work | Must | Use market rates for your own labour. Keep the working. The building surveyor and BPC may ask for it. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
co-apply | 2. Certificate of consent | Apply to the BPC with proof of ownership and ID | Must | Include your eLearning pass, construction induction card, title search and project description. There's a non-refundable application fee, so check the BPC fee schedule. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
co-receive | 2. Certificate of consent | Receive your certificate of consent | Must | Give a copy to your relevant building surveyor. It's specific to you, this land and this work. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
de-title | 3. Site, planning & design | Title search: covenants, easements, section 173 agreements | Must | These can limit what, where and how you build. Get the plan of subdivision too. | G0 | Not started |  |  |  | 01 Eligibility, Land & Planning
de-planning | 3. Site, planning & design | Check zoning & overlays and get a planning permit | If applies | Use VicPlan / Planning Property Report. Heritage, bushfire (BMO), flood, vegetation and neighbourhood character overlays often need a permit from council. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
de-survey | 3. Site, planning & design | Feature & level survey, plus a soil test (site classification) | Must | Soil classification to AS 2870 drives footing and slab design. A licensed surveyor sets out the boundaries. | G1 | Not started |  |  |  | 02 Design & Engineering
de-drawings | 3. Site, planning & design | Working drawings by a registered draftsperson or architect | Must | Include site plan, floor plans, elevations, sections, window schedule and specification. | G2 | Not started |  |  |  | 02 Design & Engineering
de-eng | 3. Site, planning & design | Structural & civil engineering by a registered engineer | Must | Covers footings and slab, framing and bracing, tie-downs, retaining walls and stormwater drainage. You need computations and certificates of compliance (design). | G2 | Not started |  |  |  | 02 Design & Engineering
de-energy | 3. Site, planning & design | Energy rating: 7-star NatHERS plus whole-of-home | Must | New Victorian homes must meet NCC 2022 energy efficiency, in force since 1 May 2024. You'll need a stamped energy report. | G2 | Not started |  |  |  | 02 Design & Engineering
de-bal | 3. Site, planning & design | Bushfire Attack Level (BAL) assessment | If applies | Required in designated bushfire prone areas. The BAL rating sets construction to AS 3959 (glazing, cladding, screens, decks). | G2 | Not started |  |  |  | 02 Design & Engineering
de-lpod | 3. Site, planning & design | Legal point of stormwater discharge from council | Must | Request it early. It can dictate drainage design and cost. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
de-easement | 3. Site, planning & design | Build-over-easement consent from the water authority | If applies | Needed if any structure sits over or near a sewer or drainage easement. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
de-siting | 3. Site, planning & design | Council report & consent for siting variations | If applies | Needed when you vary the Building Regulations siting rules (setbacks, site cover, overshadowing, fences), or for works over council assets. | G2 | Not started |  |  |  | 01 Eligibility, Land & Planning
bp-rbs | 4. Building permit & pre-start | Appoint a relevant building surveyor | Must | Get a written fee proposal. Confirm the inspection stages and what they need from you at each one. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-permit | 4. Building permit & pre-start | Obtain the building permit, naming you as owner-builder | Must | Include your certificate of consent number. The state building permit levy applies to work over $10,000. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-asset | 4. Building permit & pre-start | Council asset protection permit (and bond) | Must | Needed before any work or deliveries. Photograph the footpath, kerb, nature strip and crossover before you start. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-protect | 4. Building permit & pre-start | Protection work notices to neighbours | If applies | Needed when work could affect adjoining property, for example excavation near a boundary. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-byda | 4. Building permit & pre-start | Before You Dig Australia enquiry | Must | Locate underground services before any excavation. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-site | 4. Building permit & pre-start | Site set-up: fencing, signage, toilet, waste | Must | Display a sign with the permit number and owner-builder contact details. Secure the site against the public. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
bp-utilities | 4. Building permit & pre-start | Temporary power & water, and utility applications | Best practice | Power, water, sewer, gas and NBN connections can take months. Lodge them at permit stage. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
oh-duty | 5. Health & safety (WorkSafe Victoria) | Understand your duties as the person managing the site | Must | Provide a safe site, safe access, amenities and first aid. Consult and coordinate with every trade. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
oh-pc | 5. Health & safety (WorkSafe Victoria) | Principal contractor for projects of $350,000 or more | If applies | Appoint in writing. Duties include a health & safety coordination plan, site induction, HRCW oversight and signage. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
oh-swms | 5. Health & safety (WorkSafe Victoria) | SWMS for all high risk construction work | Must | Covers work at heights over 2 m, trenches over 1.5 m, structural alterations, work near powerlines, and more. Collect and check a SWMS before the work starts. | G3 | Not started |  |  |  | 04 Trades & Tenders
oh-cards | 5. Health & safety (WorkSafe Victoria) | Check white cards & high-risk licences | Must | Everyone on site needs a construction induction card. Crane, forklift and scaffold work need HRW licences. | G3 | Not started |  |  |  | 04 Trades & Tenders
oh-induct | 5. Health & safety (WorkSafe Victoria) | Site induction & sign-in register | Best practice | Give a 10-minute induction to every new person: hazards, amenities, emergency points and first aid. | G4 | Not started |  |  |  | 06 Site Diary & Photos
oh-asbestos | 5. Health & safety (WorkSafe Victoria) | Asbestos check before renovating or demolishing | If applies | Homes built before 1990 may contain asbestos. A licensed removalist is required above the prescribed limits. | G1 | Not started |  |  |  | 02 Design & Engineering
oh-workcover | 5. Health & safety (WorkSafe Victoria) | Register for WorkCover if you employ workers | If applies | Paying wages (not contractor invoices) can make you an employer. Contractors must carry their own cover. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
in-cw | 6. Insurance | Construction (contract works) insurance | Best practice | Covers fire, storm, theft and vandalism to the works in progress. Lenders usually require it. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
in-pl | 6. Insurance | Public liability insurance ($10m–$20m) | Best practice | Covers injury to visitors and damage to neighbours' property. Home insurance usually won't cover a construction site. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
in-pa | 6. Insurance | Personal accident / income protection | Best practice | You're the project. If you're injured, the build stops. | G3 | Not started |  |  |  | 03 Permits, Insurance & Finance
in-trade | 6. Insurance | Certificates of currency from every trade | Must | Check public liability, WorkCover (if they have employees) and domestic building insurance where required. Track the expiry dates. | G3 | Not started |  |  |  | 04 Trades & Tenders
tr-reg | 7. Engaging trades | Registered builder for trade work over $10,000* | Must | A written major domestic building contract is required. Some single-trade work (e.g. electrical, glazing) is exempt when it's the whole scope. Search the BPC practitioner register. | G3 | Not started |  |  |  | 04 Trades & Tenders
tr-lic | 7. Engaging trades | Licensed plumbers, gasfitters and electricians | Must | Plumbers are licensed or registered with the BPC. Electricians are licensed by Energy Safe Victoria. You can't do this work yourself. | G3 | Not started |  |  |  | 04 Trades & Tenders
tr-written | 7. Engaging trades | Written contract for every trade | Best practice | Include scope, price, inclusions and exclusions, program, payments, variations, defects and insurance, even for small jobs. | G3 | Not started |  |  |  | 04 Trades & Tenders
tr-abn | 7. Engaging trades | Check ABN and GST status | Best practice | Verify it on ABN Lookup. Only pay GST on invoices from GST-registered businesses. | G3 | Not started |  |  |  | 04 Trades & Tenders
cn-notify | 8. During construction | Notify the RBS at every mandatory stage | Must | Typically before placing footings, before pouring the slab, at frame and at final. Your permit may list more. Don't cover up work before it's inspected. | G4 | Not started |  |  |  | 07 Inspections & Certificates
cn-plans | 8. During construction | Build to the approved plans, or get amendments approved | Must | Changes to structure, siting or energy features need RBS approval before you build them. | G4 | Not started |  |  |  | 02 Design & Engineering
cn-pcc | 8. During construction | Plumbing compliance certificates | Must | Your plumber lodges them for prescribed plumbing work. Collect a copy for every stage (drainage, rough-in, fit-off, gas). | G4 | Not started |  |  |  | 07 Inspections & Certificates
cn-coes | 8. During construction | Certificate of Electrical Safety | Must | Your electrician issues it for all prescribed electrical work. Get a copy. | G5 | Not started |  |  |  | 07 Inspections & Certificates
cn-certs | 8. During construction | Collect product & installer certificates | Must | Includes termite management (AS 3660.1), waterproofing (AS 3740), glazing (AS 1288/2047), insulation, smoke alarms, engineer's frame and retaining-wall sign-offs, and truss certificates. | G6 | Not started |  |  |  | 07 Inspections & Certificates
cn-diary | 8. During construction | Keep a site diary & dated photos | Best practice | Record who was on site, weather, deliveries, instructions and defects. Photograph everything before it's covered. My Build does this. | G4 | Not started |  |  |  | 06 Site Diary & Photos
cn-variations | 8. During construction | Written variations before extra work | Best practice | Get the price and time impact agreed in writing first. It protects both sides. | G4 | Not started |  |  |  | 04 Trades & Tenders
fi-final | 9. Completion & occupancy | Final inspection by the RBS | Must | Hand over every compliance certificate first. A missing certificate is the most common reason a final is delayed. | G7 | Not started |  |  |  | 07 Inspections & Certificates
fi-op | 9. Completion & occupancy | Occupancy permit (new home) or certificate of final inspection | Must | You must not live in a new dwelling until the occupancy permit is issued. | G7 | Not started |  |  |  | 08 Handover, Records & Sale
fi-asset | 9. Completion & occupancy | Council asset inspection & bond refund | If applies | Repair any damage to the footpath, kerb or crossover first. | G7 | Not started |  |  |  | 03 Permits, Insurance & Finance
fi-insure | 9. Completion & occupancy | Switch to home & contents insurance | Best practice | Construction cover usually ends at completion or occupancy. | G7 | Not started |  |  |  | 03 Permits, Insurance & Finance
se-file | 10. Records & selling | Build a handover file | Best practice | Include permits, stamped plans, certificates, warranties, manuals, paint and tile codes, and as-built service locations. Keep it at least 10 years. | G7 | Not started |  |  |  | 08 Handover, Records & Sale
se-137b | 10. Records & selling | s137B defects report before any sale within 6.5 years | If applies | Commission it from a prescribed practitioner no more than 6 months before the sale. | G7 | Not started |  |  |  | 08 Handover, Records & Sale
se-ins | 10. Records & selling | Owner-builder statutory insurance before sale | If applies | Required where the work was over $20,000. Arrange it before signing the contract of sale. | G7 | Not started |  |  |  | 08 Handover, Records & Sale
se-s32 | 10. Records & selling | Disclose owner-builder work in the section 32 | If applies | Your conveyancer needs the building permit details, report and insurance. | G7 | Not started |  |  |  | 08 Handover, Records & Sale
mo-loan | 11. Finance & tax | Confirm your lender accepts owner-builders | If applies | Many don't, or they cap the loan-to-value ratio. Expect progress draws tied to stages and a valuer's inspections. | G0 | Not started |  |  |  | 03 Permits, Insurance & Finance
mo-cont | 11. Finance & tax | Budget with a 10–15% contingency | Best practice | Owner-builders commonly underestimate site works, services connections and finishes. | G1 | Not started |  |  |  | 03 Permits, Insurance & Finance
mo-fhog | 11. Finance & tax | Check First Home Owner Grant / stamp duty concessions | If applies | Owner-builders may be eligible. Check the rules and deadlines with the State Revenue Office. | G1 | Not started |  |  |  | 03 Permits, Insurance & Finance
mo-tax | 11. Finance & tax | Get tax advice on GST & CGT | Best practice | Building to live in is generally private. Building to sell can be treated as a business. Get advice early. | G0 | Not started |  |  |  | 03 Permits, Insurance & Finance

## Risks
Risk register
Likelihood × impact gives the rating. Review it weekly. Contingency is money set aside for these risks, not for upgrades.
ID | Risk | Likelihood | Impact | Score | Rating | Response | Owner | Status | Next review | Notes
R01 | Site costs blow out (rock, fill, poor soil, services) | Med | High |  |  | Soil test and feature survey before G1. Get a site-works provisional sum with a cap. | Owner-builder | Open
R02 | Key trade unavailable, program slips | High | Med |  |  | Book critical-path trades at G3. Keep a backup quote for each. | Owner-builder | Open
R03 | Trade insurance or registration lapses mid-job | Med | High |  |  | Track expiry dates in the trade register with automatic reminders. | Owner-builder | Open
R04 | Failed inspection | Med | Med |  |  | Run your own ITP checklist before calling the RBS. | Owner-builder | Open
R05 | Scope creep (upgrades) | High | Med |  |  | Freeze scope at G1. Every change goes through a written variation. | Owner-builder | Open
R06 | Owner-builder burnout or injury | Med | High |  |  | Realistic program, personal accident cover, a mentor at each gateway. | Owner-builder | Open
R07 | Wet weather | High | Low |  |  | Allow weather days in the program. Prioritise lock-up. | Owner-builder | Open

## Google Drive Map
Folder map
The folder tree for one build, in Google Drive, Dropbox or OneDrive. Paste each folder's link, or a local folder path, into Folder link; the Open links on other tabs use it. In Google Sheets the Apps Script can create the folders and fill in the links.
Code | Folder path | What goes here | Compliance stages | Gateways | Tabs that point here | Folder link (paste)
00 | 00 Project Register | This workbook, its backups and the Apps Script notes. |  | All | Every tab
01 | 01 Eligibility, Land & Planning | eLearning pass, white card, certificate of consent and application, title search, plan of subdivision, covenants, s173 agreements, Planning Property Report, planning permit, legal point of discharge, build-over-easement and siting consents. | 1, 2, 3 | G0, G1, G2 | Compliance, Gateways, Documents
02 | 02 Design & Engineering | Design brief, concept and working drawings, specification, engineering, energy (NatHERS) report, BAL assessment, feature & level survey, soil report, asbestos report, approved amendments. | 3, 8 | G1, G2 | Documents, Rooms (drawing refs), Diary (plan notes)
03 | 03 Permits, Insurance & Finance | RBS fee proposal and appointment, building permit, asset protection permit and bond, protection work notices, Before You Dig, your insurance policies, WorkSafe and principal contractor papers, loan, valuations, drawdowns, cost plan, tax advice. | 4, 5, 6, 11 | G0, G1, G3 | Project, Packages, Compliance
04 | 04 Trades & Tenders | One subfolder per trade package. In each: RFQ pack and quotes, tender comparison, signed contract and variations, licence, insurance certificates of currency and SWMS, invoices and payment records. | 5, 6, 7 | G3 to G7 | Packages, Trades, Tenders, Variations, Payments
04/01 | 04 Trades & Tenders/01 Surveyor | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/02 | 04 Trades & Tenders/02 Demolition & earthworks | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/03 | 04 Trades & Tenders/03 Plumbing & drainage | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/04 | 04 Trades & Tenders/04 Concreter | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/05 | 04 Trades & Tenders/05 Termite management | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/06 | 04 Trades & Tenders/06 Frame & truss supply | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/07 | 04 Trades & Tenders/07 Carpenter (frame) | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/08 | 04 Trades & Tenders/08 Roofing | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/09 | 04 Trades & Tenders/09 Windows & external doors | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/10 | 04 Trades & Tenders/10 Bricklayer & cladding | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/11 | 04 Trades & Tenders/11 Electrician | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/12 | 04 Trades & Tenders/12 Insulation | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/13 | 04 Trades & Tenders/13 Plasterer | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/14 | 04 Trades & Tenders/14 Waterproofer | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/15 | 04 Trades & Tenders/15 Cabinetmaker | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/16 | 04 Trades & Tenders/16 Tiler | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/17 | 04 Trades & Tenders/17 Fixing carpenter | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/18 | 04 Trades & Tenders/18 Painter | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/19 | 04 Trades & Tenders/19 Heating & cooling | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
04/20 | 04 Trades & Tenders/20 Floor coverings & landscaping | RFQ & quotes, contract & variations, licence / insurance / SWMS, invoices.
05 | 05 Selections & Specs | Product spec sheets, brochures, colour and tile codes, quotes from suppliers, orders and delivery dockets. |  | G5, G6 | Selections
06 | 06 Site Diary & Photos | Site photos (especially before anything is covered), diary exports, site induction and sign-in register. | 5, 8 | G4 to G7 | Diary, Photos
07 | 07 Inspections & Certificates | RBS inspection reports and every compliance certificate: plumbing (PCC), electrical (CoES), termite, waterproofing, glazing, insulation, smoke alarms, engineer sign-offs, commissioning sheets. | 8, 9 | G4 to G7 | Certificates, Compliance
08 | 08 Handover, Records & Sale | Occupancy permit or certificate of final inspection, warranties, manuals, as-built service locations, paint and tile codes, s137B defects report, owner-builder insurance, section 32 papers. | 9, 10 | G7 | Compliance, Certificates
99 | 99 Archive | Superseded drawings and documents, unsuccessful quotes. Never delete: move here. |  |  | Documents (status Superseded)
File naming: DocID_Description_Rev
Doc ID = folder code - document type - number, e.g. 02-DWG-012 is drawing number 12 in 02 Design & Engineering.
File name = Doc ID, then a short description with hyphens, then the revision: 02-DWG-012_Floor-Plan_RevC.pdf
Register every file in the Documents tab first. It builds the Doc ID and file name for you and tells you which folder to save it in.
Trade paperwork goes in that package's subfolder of 04, e.g. 04 Trades & Tenders/08 Roofing/04-CON-003_Roofing-Contract.pdf
When a drawing is replaced, set the old one to Superseded in Documents and move the file to 99 Archive. Never delete.
Folder links: any provider
Google Drive, Dropbox, OneDrive or SharePoint: open the folder in your browser, choose Share > Copy link, and paste it into Folder link.
Working offline on a computer? Paste the local folder path instead, e.g. C:\Users\you\Dropbox\Owner Build\02 Design & Engineering or /Users/you/Library/CloudStorage/... It opens without internet.
Google Sheets: Owner Builder > Set up Drive folders creates the folders and fills in every link for you.
Document types
DWG Drawing
SPEC Specification or spec sheet
ENG Engineering
RPT Report or assessment (soil, energy, BAL, asbestos, s137B)
APP Application
PMT Permit, consent or approval
INSP Inspection report
CERT Certificate
RFQ RFQ pack or addendum
QUO Quote or tender
CON Contract
VAR Variation
INV Invoice
REC Receipt or payment record
INS Insurance policy or certificate of currency
LIC Licence or registration
SWMS Safe work method statement
PHO Photo
COR Correspondence
FIN Finance (loan, valuation, drawdown)
PLN Plan, program or cost plan
MAN Manual
WAR Warranty
OTH Other

## Rooms
Rooms & spaces | Takeoffs
Enter each room or area once. Internal rooms get every quantity; garages skip skirting; external areas (driveways, paving, decks) get floor area only. Blank area type counts as internal. | NOTE: Include Garages and Outdoor areas where pricing and quoting is required (i.e driveways, paving etc)
Room / area | Level | Area type | Length (m) | Width (m) | Ceiling (m) | Floor area (m²) | Skirting (m) | Wall paint (m²) | Floor covering + waste (m²) | Squares | Check | Drawing ref | Notes
Kitchen / living | Ground | Internal | 7.2 | 5.4 | [8 empty] | EXAMPLE: delete this row
Driveway | External | External | 12 | 3.5 | [8 empty] | EXAMPLE: delete this row

## Selections
Selections & specs
Every product decision in one list. Lock them all in before G6 (fit-out). File spec sheets in 05 Selections & Specs. | Note: You may have a separate spec sheet from your contract but keep this here to track
Item | Category | Room | Spec / model / colour | Supplier | Qty | Unit | Unit price ($) | Total ($) | Status | Needed by | Order date | Delivery date | Spec Doc ID | Notes
Kitchen mixer tap | Fit-out | Kitchen / living | Gooseneck, brushed nickel, WELS 5-star | Plumbing supplier | 1 | ea | 420 |  | Selected | G6 |  |  |  | EXAMPLE: delete this row

## Diary
Plan notes & site diary
Who was on site, weather, deliveries, instructions, defects and questions for the building surveyor. Link notes to a drawing sheet.
Date | Type | Drawing / sheet ref | Note | On site | Weather | Trade / package | Action by | Due | Closed? | Photo Doc IDs | Notes
| Instruction to trade | A102 | Move kitchen power point 300 mm left of window as marked on site. |  |  | 11 Electrician | Electrician |  | No |  | EXAMPLE: delete this row

## Photos
Site photo log
Photograph everything before it's covered: slab mesh, frame, plumbing, insulation, waterproofing. Save the files in 06 Site Diary & Photos and log them here.
Date | Stage | Location / element | Hold point | Before covering? | Description | Doc ID / file name | Google Drive link | Notes
| G4 | Slab, north side | Pre-slab | Yes | Mesh, bar chairs and edge beam before pour | 06-PHO-001_Slab-mesh-north |  | EXAMPLE: delete this row

## Documents
Document register
Register every plan, permit, quote, contract, certificate and photo set. Pick the folder and type, type the number shown under 'Next free no.', and save the file with the name in column N.
Folder | Type | No. | Folder code | Next free no. | Doc ID | Description | Rev | Date | From / issued by | Trade package | Status | Gateway | Compliance ID | File name to use | Save in Drive folder | Folder | Check | File link | Notes
02 | DWG | 1 |  |  |  | Floor plan | C |  | Draftsperson |  | Current | G2 | de-drawings | [5 empty] | EXAMPLE: delete this row

## Tender Setup
Tender weights & recommendations
Set the scoring weights for each package (they must add to 100). The recommendation updates as you enter quotes on the Tenders tab.
Package | Budget ($) | Price % | Experience % | Program % | Quality % | Comms % | Warranty % | Total % | Compliant tenders | Recommended | Score /100 | Levelled price ($) | Over / (under) budget ($) | Lead over #2 (points) | Notes
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5
|  | 50 | 15 | 15 | 10 | 5 | 5

## Tenders
Tender comparison
One row per quote. Fail any gate and the quote is excluded. Levelling adds exclusions, provisional-sum adjustments and a risk allowance so prices are like-for-like. Scores are 0 to 10. The Check column says why a quote is excluded or needs a look.
Package | Tenderer | Received | Registered / licensed | Insurance current | ABN verified | SWMS provided | Scope conforms | Compliant? | Quoted price inc GST ($) | + Cost of exclusions ($) | ± Provisional sum adj. ($) | + Risk allowance ($) | Levelled price ($) | Experience & references | Program / availability | Quality of past work | Communication | Warranty & defects terms | Package no. | Weights row | Lowest compliant in package ($) | Median compliant in package ($) | Price points | Other points | Total /100 | Rank | Price check | Check | Key | Quote Doc ID | Notes
08 Roofing | Summit Roofing |  | Yes | Yes | Yes | Yes | Yes |  | 32500 | 1800 | 0 | 500 |  | 8 | 6 | 8 | 7 | 7 | [12 empty] | EXAMPLE: delete this row
08 Roofing | Ridgeline Metal Roofs |  | Yes | Yes | Yes | Yes | Yes |  | 36900 | 0 | 0 | 0 |  | 9 | 8 | 9 | 9 | 8 | [12 empty] | EXAMPLE: delete this row
08 Roofing | Budget Roofs Co |  | Yes | No | Yes | Yes | Yes |  | 27900 | 3500 | 1200 | 2000 |  | 5 | 9 | 5 | 4 | 5 | [12 empty] | EXAMPLE: delete this row

## Packages
Trade packages & cost control
Budget, committed (signed contracts + approved variations), paid and forecast for each package. Other tabs find a package by its two-digit No., so you can rename it safely. Type your own forecast in Forecast override if you have one.
No. | Package | Scope | Usual basis | Licence / registration | Paperwork to collect | On site from | Budget ($) | Contracted ($) | Approved variations ($) | Committed ($) | Paid ($) | Forecast override ($) | Forecast final ($) | Under / (over) budget ($) | Flag | Check | Drive folder | Folder | Notes
01 | 01 Surveyor | Surveyor: set-out & re-establishment | Lump sum | Licensed land surveyor | Set-out certificate | G4
02 | 02 Demolition & earthworks | Demolition / earthworks / excavation | Lump sum or hourly rates | Registered demolisher (if demolishing) | SWMS, tip dockets, asbestos clearance | G4
03 | 03 Plumbing & drainage | Plumber: drainage, stormwater, sewer | Lump sum per stage | BPC licensed plumber | Plumbing compliance certificate (PCC) | G4
04 | 04 Concreter | Concreter: footings & slab | Lump sum (m² + extras) | Registered if over $10k* | Engineer pour approval, pre-pour inspection | G4
05 | 05 Termite management | Termite management | Supply & install | Licensed pest controller | AS 3660.1 certificate, durable notice | G4
06 | 06 Frame & truss supply | Frame & truss supply | Supply only | n/a (supplier) | Truss & frame design certificates | G5
07 | 07 Carpenter (frame) | Carpenter: frame, fascia, eaves | Labour only or lump sum | Registered if over $10k* | Frame inspection pass | G5
08 | 08 Roofing | Roofer & plumber: roof, gutters, downpipes | Supply & install | Roof plumbing licence | PCC (roofing) | G5
09 | 09 Windows & external doors | Windows & external doors | Supply (& install) | n/a / glazier | AS 2047 / 1288 glazing certificate, energy labels | G5
10 | 10 Bricklayer & cladding | Bricklayer / cladding | Rate per 1,000 bricks or m² | Registered if over $10k* | Wall-tie & flashing photos | G5
11 | 11 Electrician | Electrician: rough-in & fit-off | Lump sum + points schedule | ESV licensed electrician | Certificate of Electrical Safety | G5
12 | 12 Insulation | Insulation | Supply & install | n/a | Insulation certificate (R-values per energy report) | G5
13 | 13 Plasterer | Plasterer | Rate per m² / lump sum | Registered if over $10k* | Wet-area board spec | G6
14 | 14 Waterproofer | Waterproofer | Lump sum per room | Registered if over $10k* | AS 3740 waterproofing certificate | G6
15 | 15 Cabinetmaker | Cabinetmaker: kitchen, vanities, robes | Supply & install | Registered if over $10k* | Shop drawings sign-off | G6
16 | 16 Tiler | Tiler | Rate per m² | Registered if over $10k* | Tile & grout codes | G6
17 | 17 Fixing carpenter | Fixing carpenter | Labour only | Registered if over $10k* | n/a | G6
18 | 18 Painter | Painter | Lump sum | Registered if over $10k* | Paint schedule & colour codes | G6
19 | 19 Heating & cooling | HVAC / heating & cooling | Supply & install | ARC refrigerant licence, electrician | Commissioning sheet, warranty | G6
20 | 20 Floor coverings & landscaping | Floor coverings, driveway, landscaping | Supply & install | Varies | Warranties | G7

## Trades
Trade register
Every trade you invite or engage. Licence and insurance dates turn amber before they expire (days set on Settings) and red once expired. Type dates as dates, e.g. 30/06/2027.
Package | Business name | Contact | Phone | Email | ABN | GST registered? | Licence / registration | Licence no. | Licence expiry | Public liability insurer | PL expiry | WorkCover | Home warranty cover (> $20k) | SWMS received | White cards checked | Status | Contract type | Contract signed? | Contract value inc GST ($) | Deposit ($) | Deposit check | Paperwork | Contract checks | Drive folder | Folder | Notes
08 Roofing | Ridgeline Metal Roofs |  |  |  |  | Yes | Roof plumbing licence |  | 2027-06-30 |  | 2027-03-31 | Yes | Yes | Yes | Yes | Engaged | Supply & install | Yes | 36900 | 1845 | [5 empty] | EXAMPLE: delete this row

## Payments
Invoices & payments
Every invoice and claim. Only rows marked Paid count towards spent to date. Don't release final payment until you have that trade's certificates.
Invoice date | Package | Trade | Invoice no. | Stage / claim | Amount inc GST ($) | GST charged? | Trade GST registered | GST check | Due | Paid? | Paid date | Retention held ($) | Invoice Doc ID | Notes
| 08 Roofing | Ridgeline Metal Roofs | 1042 | Deposit | 1845 | Yes |  |  |  | Yes |  |  |  | EXAMPLE: delete this row

## Variations
Variations
Agree the price and time impact in writing before any extra work. Approved variations add to the package's committed cost.
Var. no. | Date | Package | Trade | Description | Reason | Price impact ($) | Time impact (days) | Approval | Approved date | Signed Doc ID | Notes

## Certificates
Inspections & certificates
Mandatory inspections and the certificates the building surveyor needs at final. A missing certificate is the most common reason a final is delayed.
Type | Inspection / certificate | Standard / law | Who provides it | Package | Gateway | Requirement | Booked / requested | Passed / received | Result | Reference no. | Doc ID | Notes
Inspection | Footings (before placing footings) | Building permit | Relevant building surveyor | 04 Concreter | G4 | Must |  |  | Pending
Inspection | Pre-slab (before pouring) | Building permit | Relevant building surveyor | 04 Concreter | G4 | Must |  |  | Pending
Inspection | Frame | Building permit | Relevant building surveyor | 07 Carpenter (frame) | G5 | Must |  |  | Pending
Inspection | Other stage listed on your permit (e.g. pre-plaster, retaining wall) | Building permit | Relevant building surveyor |  | G5 | If applies |  |  | Pending
Inspection | Final inspection | Building permit | Relevant building surveyor |  | G7 | Must |  |  | Pending
Certificate | Set-out certificate |  | Licensed land surveyor | 01 Surveyor | G4 | Best practice |  |  | Pending
Certificate | Engineer pour approval / footing sign-off | AS 2870 | Structural engineer | 04 Concreter | G4 | If applies |  |  | Pending
Certificate | Plumbing compliance certificate: drainage & sewer | Building Act 1993 | Licensed plumber | 03 Plumbing & drainage | G4 | Must |  |  | Pending
Certificate | Termite management certificate & durable notice | AS 3660.1 | Licensed pest controller | 05 Termite management | G4 | Must |  |  | Pending
Certificate | Frame & truss design certificates, bracing plan | AS 1684 / AS 4440 | Frame & truss supplier | 06 Frame & truss supply | G5 | Must |  |  | Pending
Certificate | Plumbing compliance certificate: roofing | AS/NZS 3500.3 | Licensed roof plumber | 08 Roofing | G5 | Must |  |  | Pending
Certificate | Glazing certificate & energy labels (WERS) | AS 2047 / AS 1288 | Window supplier / glazier | 09 Windows & external doors | G5 | Must |  |  | Pending
Certificate | Plumbing compliance certificate: rough-in | Building Act 1993 | Licensed plumber | 03 Plumbing & drainage | G5 | Must |  |  | Pending
Certificate | Insulation certificate (R-values per energy report) | NCC 2022 | Insulation installer | 12 Insulation | G5 | Must |  |  | Pending
Certificate | Waterproofing certificate | AS 3740 | Waterproofer | 14 Waterproofer | G6 | Must |  |  | Pending
Certificate | Plumbing compliance certificate: fit-off | Building Act 1993 | Licensed plumber | 03 Plumbing & drainage | G6 | Must |  |  | Pending
Certificate | Plumbing compliance certificate: gas | Building Act 1993 | Licensed gasfitter | 03 Plumbing & drainage | G6 | If applies |  |  | Pending
Certificate | Certificate of Electrical Safety | Electricity Safety Act 1998 | Licensed electrician | 11 Electrician | G6 | Must |  |  | Pending
Certificate | Smoke alarm certificate | AS 3786 | Licensed electrician | 11 Electrician | G6 | Must |  |  | Pending
Certificate | HVAC commissioning sheet & warranty |  | HVAC installer (ARC licence) | 19 Heating & cooling | G6 | If applies |  |  | Pending
Certificate | Energy compliance (as-built matches energy report) | NCC 2022 | Energy assessor / RBS |  | G7 | Must |  |  | Pending
Certificate | Asbestos clearance certificate | OHS Regulations 2017 | Licensed asbestos assessor | 02 Demolition & earthworks | G4 | If applies |  |  | Pending
Permit | Occupancy permit or certificate of final inspection | Building Act 1993 | Relevant building surveyor |  | G7 | Must |  |  | Pending

## Settings
Settings
The legal thresholds and rules of thumb behind the checks. Update a figure here when the law changes and every tab follows.
Setting | Value | Notes
Deposit cap: contracts under the threshold | 10% | Domestic Building Contracts Act 1995
Deposit cap threshold ($) | 20000
Deposit cap: contracts at or over the threshold | 5%
Registered builder and written major domestic building contract over ($) | 10000 | An increase to $20,000 has been proposed. Change it here if it's adopted.
Home warranty cover required over ($) | 20000 | First Resort Home Warranty Scheme, contracts signed from 1 July 2026
Certificate of consent required over ($) | 20000 | Was $16,000 before 1 July 2026
Principal contractor required from ($) | 350000 | OHS Regulations 2017
Warn about expiring licences and insurance (days ahead) | 30
Flag quotes this far under the median | 15% | Something is probably missing from the quote
Flag packages forecast over budget by more than | 5%
G3 target: share of package budgets committed | 80% | G3 exit check
Default ceiling height (m) | 2.55 | Used on Rooms when Ceiling is blank
Floor covering waste allowance | 10% | Used on Rooms
Victorian rules checked September 2026. General information, not legal advice.

## Lists (hidden)
Gates | YesNo | YesNoNA | Status | Requirement | GateItemType | Decision | SelectionStatus | SelectionCategory | DiaryType | HoldPoint | FolderCode | DocType | DocStatus | TradeStatus | VariationStatus | VariationReason | CertType | Result | LowMedHigh | RiskStatus | Level | AreaType | ContractType | Doc type | Meaning
G0 | Yes | Yes | Not started | Must | Entry criteria | Go | To choose | Base | Site diary | Footings | 00 | DWG | Draft | Invited | Pending | Owner change | Inspection | Pending | Low | Open | Ground | Internal | Lump sum (fixed price) | DWG | Drawing
G1 | No | No | In progress | If applies | Deliverable | Hold | Selected | Frame & roof | Plan note | Pre-slab | 01 | SPEC | Current | Quoted | Approved | Site condition | Certificate | Pass | Med | Watching | First | Garage | Schedule of rates | SPEC | Specification or spec sheet
G2 |  | N/A | Done | Best practice | Exit check | Stop | Ordered | Lock-up | Instruction to trade | Frame | 02 | ENG | Superseded | Engaged | Rejected | Design change | Permit | Fail | High | Closed | Second | External | Labour only | ENG | Engineering
G3 |  |  | N/A |  |  |  | Delivered | Services | Defect | Insulation | 03 | RPT |  | Complete |  | Authority requirement |  | N/A |  |  | Basement |  | Supply only | RPT | Report or assessment (soil, energy, BAL, asbestos, s137B)
G4 | [6 empty] | Installed | Fit-out | Question for RBS | Waterproofing | 04 | APP |  | Not engaged |  | Other |  |  |  |  | External |  | Supply & install | APP | Application
G5 | [7 empty] | Appliances | Variation request | Pre-plaster | 05 | PMT | [10 empty] | Cost plus / do & charge | PMT | Permit, consent or approval
G6 | [7 empty] | External |  | Final | 06 | INSP | [11 empty] | INSP | Inspection report
G7 | [7 empty] | Other |  | Other | 07 | CERT | [11 empty] | CERT | Certificate
[11 empty] | 08 | RFQ | [11 empty] | RFQ | RFQ pack or addendum
[11 empty] | 99 | QUO | [11 empty] | QUO | Quote or tender
[12 empty] | CON | [11 empty] | CON | Contract
[12 empty] | VAR | [11 empty] | VAR | Variation
[12 empty] | INV | [11 empty] | INV | Invoice
[12 empty] | REC | [11 empty] | REC | Receipt or payment record
[12 empty] | INS | [11 empty] | INS | Insurance policy or certificate of currency
[12 empty] | LIC | [11 empty] | LIC | Licence or registration
[12 empty] | SWMS | [11 empty] | SWMS | Safe work method statement
[12 empty] | PHO | [11 empty] | PHO | Photo
[12 empty] | COR | [11 empty] | COR | Correspondence
[12 empty] | FIN | [11 empty] | FIN | Finance (loan, valuation, drawdown)
[12 empty] | PLN | [11 empty] | PLN | Plan, program or cost plan
[12 empty] | MAN | [11 empty] | MAN | Manual
[12 empty] | WAR | [11 empty] | WAR | Warranty
[12 empty] | OTH | [11 empty] | OTH | Other